## Must Read
CONFIDENTIAL SUBJECT TO NDA
Lambda ¦ Pegatron GB200 tracker
Document release to Supplier: 12/05/2024
Rev 1 12/05/2024
The information contained within this CRD is considered confidential and proprietary information. Suppliers are required to maintain this document and its information as confidential, and not make use thereof other than for the purpose of responding to this CRD. This CRD is provided for the exclusive use of the supplier and copies shall not be made available to any other parties, externally or internally without our express written consent. By accepting this document, you agree to the terms of confidentiality and all terms contained herein, and also agree to impose such terms on any employee or business partners given access to the information. If you are unable to adhere to these terms of confidentiality please immediately return this document and delete or destroy all copies you have made. Lambda reserves the right to make revisions or cancel this CRD at Lambda’s sole discretion. This CRD may not result in any award of business. Lambda will only pay for the goods or services that are ordered using an authorized Purchase Order and delivered to the locations listed on the Purchase Order.

## Data Hall Info
Address | 2510 Zanker Rd., San Jose, CA
Custom brokerage personnel name
Custom brokerage personnel phone number
Custom brokerage personnel email
Receiving personnel name
Receiving personnel phone number
Receiving personnel email
Is lift required?
Operating Hours
Special requirement
Entity name
Business Registration Number / Tax ID
Custom ID

## Milestone (hidden)
Start Date | End Date | Milestone | Owner
|  | Place Zero-Dollar Purchase Order | Lambda
|  | System Production | Pegatron
|  | System Shipment | Pegatron
|  | System Delivery | Pegatron
|  | Rack-and-stack | Lambda
|  | On-site (Zanker) Setup | Pegatron
|  | Power on | Pegatron

## XFN Team
Pegatron | Name | Email | Phone | Location
PJM | Ryker Huang | Ryker_Huang@pegatroncorp.com |  | Taiwan
PM | Vincent Chen | Vincent_Chen@pegatroncorp.com |  | Taiwan
HW Engineering | Kevin Done | Kevin_Done@pegatroncorp.com |  | Fly to San Jose
SW Engineering | Brian Yeh | Brian_Yeh@pegatroncorp.com |  | Fly to San Jose
Thermal & L10 Engineering | Stanley Huang | Stanley_Huang@pegatroncorp.com |  | Taiwan
Thermal & L10 Engineering | Wilson Huang | Wilson8_Huang@pegatroncorp.com |  | Taiwan
Sales | Alvin Fan | Alvin_Fan@pegatroncorp.com |  | Taiwan
Sales | William Chen | William3_Chen@pegatroncorp.com | 510-402-9510 | Fremont
Lambda | Name | Email | Phone | Location
PM | Maxx Garrison | maxx@lambdal.com |  | Remote
HPC Engineering | Rich Underwood | rich@lambdal.com |  | Remote
HPC Engineering | Rich Tisor | richard@lambdal.com |  | San Jose
DC Infrastructure | Alee Fong | alee@lambdal.com |  | San Jose
Supply Chain | Doris Rainbow | doris@lambdal.com |  | San Jose
Technical Sourcing | Fred Feng | fred.feng@lambdal.com | 516-450-0726 | San Jose

## L10 BOM
Item | Item Description | Vendor | Qty per System
L6 | NCT 1U System Compute Tray | Chenbro | 1
L6 | PCBA (w/o Nvidia parts like Bianca/HMC/BF3/CX7 module; small boards only; excluding MVA) | Pegatron | 1
L6 | Inner Busbar (R+L) | Amphenol | 1
L6 | Cold Plate (R+L) | Cooler Master | 1
L6 | Inner Manifold (L+R) | Cooler Master | 2
L6 | 4056 FAN | Sunon | 8
L6 | PDB HSK Assy | Cooler Master | 1
L6 | Cable set (24 calbes) | VSO & Amphenol | 1
L10 | L6 System (1U System, PCBA, Fans, Cold Plate, Cable Set) | Pegatron | 1
L10 | 2x CX7 Mezz, Crypto enabled; 900-24768-0002-000 | Nvidia | 2
L10 | Bianca 900-2G548-0001-000 | Nvidia | 2
L10 | HMC; 900-24764-0000-000 | Nvidia | 1
L10 | BF3 dual port card; 900-9D3B6-00CN-PA0 | Nvidia | 2
L10 | M.2 22110 SSD; Samsung PM9A3 (MZ1L21T9HCLS-00A07) 1.92TB | Samsung | 1
L10 | E1.S SSD; Samsung PM9A3 (MZTL23T8HCLS-00A07) 3.84TB | Samsung | 8
L10 | E1.S Latch (15mm, 1302-04TQ000；HEMMING/P7-E1S-150-000) | Chenbro | 8
Accessory | Pegatron Linking Board + 4200W PSUx2 | Pegatron | 1

## GB200 L10 shipment schedule
| Item | Schedule | Owner | Location | WW50 | [6 empty] | WW51 | [6 empty] | WW52
[5 empty] | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29
| L10 sample Ship out | 2024-12-10 | Pega | TY2 | 2024-12-10: L10 sample ship out by Air
| 6KW Dry cooler(AURAS) ship out | 2024-12-11 | Pega | HQ | 2024-12-11: 6KW Dry cooler ship out
| 6KW Dry cooler(AURAS) arrive at PUSA | 12/13 -> 12/19 | Pega | PUSA | 2024-12-19: 6KW Dry cooler arrive at PUSA
| L10 sample arrive at Lambda | 12/13 -> 12/16 | Pega | Zanker | 2024-12-16: L10 sample arrive at Lambda
| Dry cooler install PG25 | 12/16 -> 12/20 | Pega | Zanker | 2024-12-20: Dry cooler install PG25
| L10 recheck and setting | 12/18~12/20 | Pega | Zanker | 2024-12-18: L10 recheck and setting
| L10 power on and set-up env. | 2024-12-23 | Pega | Zanker | 2024-12-23: L10 power on and set-up env.
HW | on site support/EE and Technical discussion, Mechnical and cable routing support | 12/10~12/24 | Pega/Kevin Done | Zanker | bar: 2024-12-11 to 2024-12-24
SW | on site support/Bios/BMC requirement discussion and on site debug | 12/10~12/24 | Pega/Brian Yeh | Zanker | bar: 2024-12-10 to 2024-12-24
| Lambda HPC Engineering onsite | 12/10~12/23 | Rich Tisor | Zanker | bar: 2024-12-10 to 2024-12-13; 2024-12-16 to 2024-12-20; 2024-12-23 to 2024-12-24
| Lambda Infrastructure onsite | 12/10~12/23 | Alee Fong | Zanker | bar: 2024-12-10 to 2024-12-13; 2024-12-16 to 2024-12-20; 2024-12-23 to 2024-12-24
| Lambda Supply Chain onsite | 12/10~12/23 | Fred Feng | Zanker | bar: 2024-12-10 to 2024-12-13; 2024-12-16 to 2024-12-20; 2024-12-23 to 2024-12-24
| Lambda HPC engineering onsite | 12/17~12/19 | Rich Underwood | Zanker | bar: 2024-12-16 to 2024-12-18
[7 empty] | Assume: | 1. need sales to check with customer, what kind of support
2. ERoT not ready enable at EVT stage(BMC card doesn't support security)
3. NV Diag status - ongoing
4. NV Qual status - ongoing
12/16 Meeting follow-ups:
- Pegatron to share VBIOS image
- Pegatron to share performance testing result & SOP
| User name | root
| Password | abcdef

## GB200 L11 shipment schedule
[12 empty] | WW03 | [6 empty] | WW04 | [6 empty] | WW05 | [6 empty] | WW06
|  | Milestone | Schedule | Owner | Location | time axis 2025-01-07 to 2025-02-27
|  | Rack sample Ship out - ship to Zanker | 2025-01-10 | Pegatron | TY2 | 2025-01-10: 1/10 Rack sample ship out by Air; 2025-01-27: CNY
|  | Audit colo (Mountain View) | 2025-01-11 | Lambda |  | 2025-01-10: Audit colo (Mountain View)
|  | Rack sample arrive at US | 2025-01-16 | Pegatron | PUSA | 2025-01-16: Rack sample arrive at US
|  | Rack sample arrive at Lambda | 2025-01-17 | Pegatron |  | 2025-01-17: Rack sample arrive at Lambda
|  | Rack recheck and setting, Install PG25 | 1/17 ~ 1/21 | Pegatron |  | 2025-01-20: Rack recheck and setting, Install PG25
|  | Rack power on and set-up env. | 1/22 ~ 1/24 | Pegatron |  | 2025-01-22: 1/22 ~ 1/24 L11 Bring up(HW)
|  | NVL72 system Bring up(SW) | 1/27 ~ 2/7 | Pegatron |  | 2025-01-27: 1/27 ~ 2/7 NVL72 system Bring up(SW)
|  |  | 1/15 ~ 1/18 | Huberson Su | bar: 2025-01-15 to 2025-01-18
2025-01-01 | DM1 | on site support/EE and Technical discussion | 1/15 ~ 1/25 | Cacique Chen | bar: 2025-01-15 to 2025-01-25
2025-01-02 | DM2 |  | 1/23 ~ 2/7 | Terry Su | bar: 2025-01-23 to 2025-02-07
3 | ME | on site support/ Mechanical (L10 & L11) | 1/18 ~ 1/25 | Wilson Yu | bar: 2025-01-18 to 2025-01-25
4 | Cable | on site support/ Cable routing support (L10 & L11) | 1/18 ~ 1/25 | Ariel Lee | bar: 2025-01-18 to 2025-01-25
5 | Thermal | on site support/Install PG25 and recheck | 1/18 ~ 1/25 | Wilson8 Huang | bar: 2025-01-18 to 2025-01-25
6 | BIOS/BMC | on site support/Bios requirement discussion and on site debug | 1/18 ~ 1/31 | Ivan Lee | bar: 2025-01-19 to 2025-02-07
7 | Networking |  | 1/18 ~ 2/7 | Thomas Chu | bar: 2025-01-18 to 2025-02-07
2nd | if need
1 | DM/EE | bar: 2025-02-07 to 2025-02-21
2 | FW | bar: 2025-02-07 to 2025-02-21
3 | ME/Thermal | bar: 2025-02-07 to 2025-02-21

## FWSW revisions
GB200 EVT L10 FW/SW version |  |  |  | GB200 EVT L10/L11 FW/SW version
Date | 2024-12-11 |  |  | Date | Jan 2025
Item | Firmware | Version | Note | Item | Firmware | Version | Note
1 | Pega BMC | 0.01.04 |  | 1 | Pega BMC | 0.01.06
2 | Pega BMC EROT | N/A |  | 2 | Pega BMC EROT | N/A
3 | HGX_FW_BMC | GB200Nvl-24.10-9 |  | 3 | HGX_FW_BMC | GB200Nvl-24.11-1
4 | HGX_FW_EROT | 01.03.0250.0000_n04 |  | 4 | HGX_FW_EROT | 01.03.0250.0000_n04
5 | HGX_FW_CPLD | 0.1C |  | 5 | HGX_FW_CPLD | 0.1C
6 | Pega SBIOS | 00.01.04 |  | 6 | Pega SBIOS | 00.01.08
7 | Bianca FPGA | 1.16 |  | 7 | Bianca FPGA | 1.1C
8 | GB200 VBIOS | 97.00.52.00.02 |  | 8 | GB200 VBIOS | 97.00.67.00.01
9 | E1.S CPLD | 0B.03.04 |  | 9 | E1.S CPLD | 0B.03.04
10 | IPEX CPLD | V10.01.0F |  | 10 | IPEX CPLD | V10.01.0F
11 | CX7 FW | 28.42.1224 |  | 11 | CX7 FW | 28.42.1242
12 | BF3 FW | 32.42.1000 |  | 12 | BF3 FW | 32.42.1000
Item | Software/Driver | Version | Note | Item | Software/Driver | Version | Note
1 | Compute OS | Ubuntu22.04 RHEL 9.4 |  | 1 | Compute OS | Ubuntu22.04 RHEL 9.4
2 | GPU(GB200) | 570.26 |  | 2 | GPU(GB200) | 570.44
3 | DPU(BF3) | 2.8.0 (including 24.07-0.6.1.0, MLX5 core) |  | 3 | DPU(BF3) | 2.8.0 (including 24.07-0.6.1.0, MLX5 core)
4 | NIC (CX7) | 24.07-0.6.1.0 |  | 4 | NIC (CX7) | 24.07-0.6.1.0
5 | NIC (I210-AT) | igb-5.17.4 |  | 5 | NIC (I210-AT) | OS Native
6 | VGA (AST 2600) | 1.14.4 |  | 6 | VGA (AST 2600) | 1.14.4

## FRU List (hidden)
| FRU part | Description | Lambda % | SMC % | Spare Qty | Replenishment Lead Time (Taiwan) | Replenishment Lead Time (US)
MCIO | AOM-DP801-IO-P | IO board for Delta-Next GPU system,RoHS |  |  | 34
NIC Riser | AOM-DP801-PCIE-P | NIC Riser board(After Mid-Plane) for Delta-Next GPU Syst |  |  | 34
NIC Adapter | AOM-DP801-SW-P | NIC adaptor board with PLX switch for Delta-Next GPU sys |  |  | 140
| AOM-DXF-IO-P | Delta Next IO module, VGA, RJ45 LAN, USB3.0, COM, UID,Ro |  |  | 34
| AOM-GP801-LPIO-P | NIC card carrier board for Delta-Next GPU system,RoHS |  |  | 34
| AOM-SXM5-IO-P | PCIE Gen5 switch board for 4U 8 SXM5 GPU system,RoHS |  |  | 34
| BPN-GPU-GP801 | Midplane for 8U Delta-Next GPU system SYS-821GE-TNART (c |  |  | 34
Fan | FAN-0238L4-1 | 80x80x80 mm, 12K-11.3K RPM Counter-rotating Fan for GP801,Ro |  |  | 145
Fan | FAN-0246L4 | 80x80x80mm, 48V 14.6K/12.2K RPM Counter-rotator, rear fan, c |  |  | 70
GPU | GPU-NVHGX-H100-88 | NVIDIA DELTA-NEXT HGX GPU Baseboard, 8 H100 80GB SXM5 |  |  | 34
M.2 | HDS-MMN-MTFDKBG1T9TFR1BC | Micron 7450 PRO 1.9TB NVMe PCIe 4.0 M.2 22x110mm 3D TLC, |  |  | 34
Motherboard | MBD-X13DEG-OAD-P | X13 4U/8U Delta Next SXM5 GPU Eagle Stream DP MB |  |  | 34
DRAM | MEM-DR564L-HL01-ER48 | 64GB DDR5-4800 2Rx4 LP (16Gb) ECC REG DIMM, HF, RoHS |  |  | 34
PSU | PWS-3K06G-2R | AC-DC 3000W, Titanium efficiency, DC output: 54Vdc/45A |  |  | 109
Motherboard | MBD-X13DEG-OAD-P | X13 4U/8U Delta Next SXM5 GPU Eagle Stream DP MB |  |  | 40